## Sheet1
PRINCE ALBERT MUNICIPALITY
MSCOA PROJECT PLAN FOR IMPLEMENTATION
No | Project Name | Resource/Responsible Person | Finish Date
1 | Project Initiation ( Champion ) | J.Neethling ( CFO ) | Ongoing
2 | Steering Committee | Chief Financial Officer | Ongoing
Municipal Manager
Acting Manager: Technical Services
Manager: Corporate Services
3 | Project Team | J Neethling/ H Mettler/ A Vorster | Ongoing
D Plaatjies/ C Baadjies/ S Windvool/ D Sarelse
D. Mooneys/ S.Antonie/A.Jacobs
Work Streams
No | Project Name | Resource/Responsible Person | Finish Date
1 | Vote Structure | CFO / Mubesko Africa | 2017-05-31
| Review the current municipal chart of accounts | CFO / Mubesko Africa | 2017-03-31
| Align function to MSC & identify anomalies | CFO / Mubesko Africa | 2017-03-31
| Line by Line Comparison of the Item segment | CFO / Mubesko Africa | 2017-03-31
| DefineFunding Sources & link to Item Segment | CFO / Mubesko Africa | 2017-03-31
| DefineRegional Indicators and provide to mSCOA Team | CFO / Mubesko Africa | 2017-03-31
| DefineOperations & Capital Projects, including Repairs & Maintenance | CFO / Mubesko Africa | 2017-03-31
| Compilation of Detail Budgets - SCOA classification across segments (2016/17 MTREF) | CFO / Mubesko Africa | 2017-03-31
2 | IT Infrastructure & Network | CFO / Ubertech | 2017-03-28
3 | Data Cleansing & Gap Analysis | CFO / Fujitsu | Ongoing
4 | HR & Payroll | CFO / Fujitsu | 2017-05-31
5 | Planning (IDP & Budget) | CFO / Vorster / Mubesko | 2017-02-28
6 | Financial Management | CFO / Mubesko Africa | Ongoing
| Financial Accounting (BP 3) | CFO / Mubesko Africa | Ongoing
| Costing & Reporting (BP 4) | CFO / Mubesko Africa
| Treasury & Cash Management (BP 6) | CFO / Mubesko Africa | Ongoing
| Grant Management (BP 8) | CFO / Mubesko Africa | Ongoing
7 | Procurement Cycle | CFO /Christa / Donovan | Ongoing
8 | Revenue | CFO / Shirley | 2017-07-01
| Real Estate & Resource Management (BP 10) | Anneleen
| Land use & Building control Management (BP 12) | CFO / Shirley / Vorster
| Valuation Roll (BP 13) | CFO/ Shirley
| Revenue Cycle: Meter Reading, Billing, Accounts Receivable; Revenue Management & Receipting (BP 14) | CFO/ Shirley
| Customer Care, Credit Control & Debt Collection (BP 15) | CFO/ Shirley
9 | Assets | CFO/ MM / Engieer / Danvor | 2017-03-31
10 | Internal Audit and Corporate Identity | CFO / Moore Stephens | Ongoing
| Collate Project Documentation for Audit File | CFO / Moore Stephens | Ongoing
11 | SDBIP and Performance Management | Vorster / MM / Moore Stephens | Ongoing
12 | Training | All | Ongoing
13 | Reporting | CFO / Donovan | Ongoing
14 | Project Close-out Report | CFO /Mubesko | December 2018